ENGINEERING DELIVERY PLAYBOOK

# U-GETMO Software Delivery Roadmap

A production-focused SDLC for moving from MVP to a reliable e-commerce platform

Aligned to AI-SWE-001 and AI-SWE-002

| Current maturity | Level 1 - MVP |
| --- | --- |
| Target maturity | Level 2 - Production System |
| Planning horizon | 12 weeks plus controlled rollout |
| Primary outcome | Validated, observable, recoverable and safely deployable commerce system |

Version 1.0 | 27 August 2026 | Engineering working plan

# Executive direction

Delivery decision: Use a gated 12-week programme made of bounded, dependency-aware work units. Do not treat production hardening as one large task, and do not build dependent features on top of failed or unverified security, data, payment or deployment foundations.

U-GETMO has a credible MVP foundation: customer and administrator experiences, product discovery, cart, wishlist, profile, order, supplier and payment-adjacent workflows are represented. The next stage is not primarily additional feature breadth. It is establishing trusted security boundaries, commerce correctness, controlled delivery, operational visibility and recovery evidence.

## Programme objective

- Secure: authenticated and authorized at trusted server boundaries.

- Correct: pricing, discounts, stock, payments and order transitions are server-authoritative and testable.

- Deployable: every release is built, tested, promoted and rolled back through a controlled pipeline.

- Observable: failures can be detected, correlated and diagnosed before customer complaints become the monitoring system.

- Recoverable: backups, restoration, migrations and rollback are rehearsed rather than assumed.

- Maintainable: architecture, decisions, risks, validation and next actions remain discoverable across sessions and team changes.

# 1. SDLC operating model

Governing loop: Load state -> choose a dependency-ready work unit -> define success -> implement -> validate -> correct failures -> record decisions -> update state -> continue.

## 1.1 Completion states

| State | Meaning |
| --- | --- |
| Work Unit Complete | The acceptance criteria have been implemented. |
| Work Unit Validated | The required automated and review checkpoints have passed. |
| Phase Complete | Every required work unit in the phase is complete and validated. |
| System Implementation Complete | The required implementation scope exists; cross-system proof may still be pending. |
| System Validated | Required end-to-end, security, operational and recovery validation has passed. |
| Production Ready | The production readiness gate is approved by accountable business and engineering owners. |

## 1.2 Non-negotiable rules

- Executed does not mean verified.

- A failed foundational checkpoint blocks affected downstream work.

- Requirement, architecture and security changes must be impact-assessed and recorded.

- Human approval is proportional to risk; irreversible or production-critical actions require explicit authorization.

- Work units must be meaningful engineering outcomes, not giant tasks or file-by-file microtasks.

- Project state is updated after every meaningful validated transition.

# 2. Persistent project structure

Create the following documentation structure alongside the application. The issue tracker remains the detailed execution system; these files preserve engineering continuity and architecture.

docs/ ¦-- project/ ¦ ¦-- PROJECT_STATE.md ¦ ¦-- ROADMAP.md ¦ ¦-- RISKS.md ¦ ¦-- DECISIONS.md ¦ `-- TECHNICAL_DEBT.md ¦-- requirements/ ¦ ¦-- product-requirements.md ¦ ¦-- business-rules.md ¦ `-- non-functional-requirements.md ¦-- architecture/ ¦ ¦-- system-context.md ¦ ¦-- component-architecture.md ¦ ¦-- data-model.md ¦ ¦-- api-contracts.md ¦ ¦-- authentication-authorization.md ¦ ¦-- payment-order-lifecycle.md ¦ ¦-- supplier-integrations.md ¦ `-- threat-model.md ¦-- adr/ ¦-- testing/ ¦-- operations/ `-- releases/

## 2.1 Minimum PROJECT_STATE.md content

- Project objective and maturity target

- Current architecture and development phase

- Completed, active, pending and blocked work

- Architectural and technical decisions

- Dependencies, constraints and assumptions

- Known issues and technical debt

- Changed contracts, migrations, dependencies and configuration

- Validation status and failing checks

- Deployment and security implications

- Next recommended work unit

# 3. Delivery workstreams and ownership

| Workstream | Accountable lead | Scope |
| --- | --- | --- |
| Security and identity | Security/backend | Sessions, token verification, RBAC, ownership, secrets, API controls, abuse protection |
| Commerce correctness | Backend/product | Pricing, coupons, stock, cart, checkout, payment and order-state integrity |
| Backend and data | Backend/data | Services, schema, constraints, transactions, migrations, retention, audit and backups |
| Frontend quality | Frontend/UX | Failure states, accessibility, performance, type safety and client/server boundaries |
| Supplier integrations | Integration owner | Amrod, Parrot, Tarsus, uploads and data-normalization reliability |
| Payments | Backend/finance | Payment initiation, callbacks, idempotency, reconciliation, refunds and support controls |
| Quality engineering | QA/engineering | Unit, integration, contract, component, end-to-end, security and recovery tests |
| Platform and delivery | Platform/DevOps | Environments, secrets, CI/CD, infrastructure, deployment and rollback |
| Operations | Service owner | Logging, monitoring, alerts, incidents, SLOs, recovery and support |

## 3.1 Decision authority

- Product owner: scope, acceptance, customer impact and launch decision.

- Engineering lead: architecture, sequencing, quality and technical risk.

- Security owner: identity, secrets, API/data controls and risk acceptance.

- Platform owner: hosting, delivery, observability, recovery and operational readiness.

- Data/backend owner: model, migrations, transactions, ownership and retention.

- Payments/finance owner: settlement, reconciliation, refunds, provider configuration and financial controls.

# 4. Twelve-week roadmap overview

| Phase | Timing | Objective | Primary outcome |
| --- | --- | --- | --- |
| 0 | 0-48 hours | Security containment | Rotate exposed supplier secret; restrict unsafe proxies; preserve incident evidence |
| 1 | Week 1-2 | Requirements and architecture | System context, threat model, role matrix, data/payment/integration decisions |
| 2 | Week 2-4 | Trusted security boundaries | Verified sessions, backend authorization, explicit APIs, validation and abuse controls |
| 3 | Week 3-6 | Quality and release foundation | Test harnesses, CI/CD, staging, typed environments and immutable releases |
| 4 | Week 5-8 | Commerce and integration hardening | Pricing, stock, order, payment, supplier and upload correctness |
| 5 | Week 7-10 | Observability and reliability | Logs, errors, metrics, SLOs, alerts, timeouts, retries and runbooks |
| 6 | Week 9-12 | Recovery and production validation | Backups, restore, rollback, load, accessibility, security and readiness review |

Parallelism rule: Independent workstreams may proceed in parallel only when their upstream contracts are sufficiently complete and validated. Security containment begins immediately; architecture, test infrastructure and environment work can overlap after dependencies are explicit.

# 5. Phase plans and exit checkpoints

## Phase 0 - Security containment

Duration: 0-48 hours

Objective: Reduce immediate exposure before further feature work propagates risk.

### Work units and outputs

- SEC-001: Rotate or revoke the exposed supplier credential; do not reproduce it in tickets or documentation.

- SEC-002: Remove the credential from source and repository history; configure secret scanning.

- API-001: Disable or restrict unauthenticated supplier write/delete proxy operations.

- SEC-003: Review supplier logs and record whether incident escalation is required.

- STATE-001: Create project state, risk register and containment completion record.

### Exit checkpoint

- [ ] Old credential is unusable and replacement exists only in managed server-side secrets.

- [ ] No public route exposes unrestricted supplier write capability.

- [ ] Incident evidence and residual risk are recorded.

## Phase 1 - Requirements and architecture baseline

Duration: Week 1-2

Objective: Resolve the foundational decisions on which security, data, payment and delivery work depend.

### Work units and outputs

- ARCH-001: Document system context, components, external dependencies and trust boundaries.

- AUTHZ-001: Define customer, business and administrator permissions plus record ownership rules.

- DATA-001: Define entities, identifiers, relationships, constraints, transaction boundaries and retention.

- PAY-001: Define the order/payment state machine, callback rules, idempotency and reconciliation.

- INT-001: Inventory required supplier routes, credentials, limits, caching and failure behavior.

- NFR-001: Approve availability, performance, security, privacy, RPO and RTO requirements.

- ARCH-002: Record session, authorization boundary, hosting and deployment decisions as ADRs.

### Exit checkpoint

- [ ] Architecture and business rules are approved by accountable owners.

- [ ] Critical unknowns have owners and deadlines.

- [ ] No dependent work relies on an unresolved high-impact decision.

## Phase 2 - Trusted security boundaries

Duration: Week 2-4

Objective: Ensure that identity, permissions, secrets and APIs are enforced at trusted server boundaries.

### Work units and outputs

- AUTH-001: Cryptographically verify token/session authenticity, issuer, audience and expiry.

- AUTH-002: Adopt server-set HttpOnly, Secure and SameSite session cookies or an approved equivalent.

- AUTHZ-002: Enforce backend RBAC and per-resource ownership checks.

- API-002: Replace wildcard proxies with explicit allowlisted application endpoints.

- API-003: Add server-side body, query, path, file and content-type validation.

- SEC-004: Add endpoint-specific rate limits, brute-force controls and payload limits.

- SEC-005: Add CSRF controls, security headers and safe error responses.

### Exit checkpoint

- [ ] Forged, expired, wrong-audience and modified tokens are rejected.

- [ ] Cross-user and cross-role access tests pass.

- [ ] Unknown paths, methods, large payloads and unauthenticated writes are denied.

## Phase 3 - Quality and release foundation

Duration: Week 3-6

Objective: Make every change mechanically verifiable and every release repeatable.

### Work units and outputs

- TEST-001: Establish unit and component testing.

- TEST-002: Establish isolated API/backend integration testing.

- TEST-003: Establish end-to-end testing for critical customer and admin journeys.

- CICD-001: Require clean install, environment validation, typecheck, lint, tests and production build.

- CICD-002: Add secret, dependency and static-security checks.

- ENV-001: Define typed configuration for development, test, staging and production.

- REL-001: Produce immutable, versioned artifacts and automated staging deployments.

### Exit checkpoint

- [ ] Every pull request passes required automated checks.

- [ ] Critical security and commerce regressions block merging.

- [ ] A clean staging deployment is reproducible without a developer machine.

## Phase 4 - Commerce and integration hardening

Duration: Week 5-8

Objective: Prove correctness for financial, order, stock and supplier failure scenarios.

### Work units and outputs

- COM-001: Make product price, coupon, tax, shipping and payable amount server-authoritative.

- COM-002: Define stock conflict, concurrent-cart and order transition behavior.

- PAY-002: Verify payment request integrity and provider callback authenticity.

- PAY-003: Implement idempotent checkout/callback processing and duplicate prevention.

- PAY-004: Implement reconciliation, refund, cancellation and long-pending transaction procedures.

- INT-002: Add supplier timeouts, response validation, safe retries and degradation behavior.

- FILE-001: Authorize, validate, scan, retain and delete uploaded artwork/files safely.

### Exit checkpoint

- [ ] Client manipulation cannot change payable amounts or protected order state.

- [ ] Duplicate requests cannot duplicate financial or stock effects.

- [ ] Supplier outages degrade safely and payment/order records reconcile.

## Phase 5 - Observability and reliability

Duration: Week 7-10

Objective: Detect, diagnose and respond to failures across critical customer transactions.

### Work units and outputs

- OBS-001: Add structured, redacted logs and correlation IDs.

- OBS-002: Add centralized frontend/server error tracking with release association.

- OBS-003: Add traffic, latency, error, dependency and commerce metrics.

- OBS-004: Define dashboards, SLOs, alerts, owners and escalation paths.

- REL-002: Add explicit outbound dependency timeouts.

- REL-003: Define bounded retry and idempotency policies.

- REL-004: Add health/readiness checks and incident runbooks.

### Exit checkpoint

- [ ] Critical workflow failures trigger actionable alerts.

- [ ] Support can trace login-to-order activity using a safe reference ID.

- [ ] Dependency-failure exercises pass without data corruption or false success.

## Phase 6 - Recovery and production validation

Duration: Week 9-12

Objective: Prove that the system can launch safely, recover from failure and be operated by assigned owners.

### Work units and outputs

- DATA-002: Automate and monitor database/object backups.

- DATA-003: Rehearse restoration and record achieved RPO/RTO.

- REL-005: Rehearse deployment rollback and migration roll-forward/rollback strategy.

- PERF-001: Set frontend bundle/Core Web Vitals budgets and load-test critical APIs.

- A11Y-001: Complete keyboard, screen-reader, contrast, focus and reduced-motion review.

- SEC-006: Complete final security review and verify remediation.

- E2E-001: Complete production-like regression and operational exercises.

- GATE-001: Conduct formal Production Readiness Review and approve or block launch.

### Exit checkpoint

- [ ] Restoration and rollback evidence meets agreed objectives.

- [ ] Performance, accessibility, security and end-to-end criteria pass.

- [ ] No critical blocker remains and launch approval is recorded.

# 6. Dependency-aware execution graph

| Work boundary | Required predecessor | Unlocks |
| --- | --- | --- |
| Project state + containment | None | Architecture and security planning |
| Requirements + architecture | State and accountable decisions | Data, identity, payment, API and test design |
| Data and business contracts | Approved architecture | Backend services and migrations |
| Verified identity + authorization | Role/ownership model | Protected APIs and admin/customer integration |
| Backend/API behavior | Data, identity and business rules | Frontend integration and contract tests |
| Automated test and CI foundation | Environment and contract decisions | Controlled staging releases |
| Integrated commerce system | Validated API + frontend | E2E, performance, security and recovery testing |
| System validation | All phase gates | Production Readiness Review |

Blocking rule: When a checkpoint fails, determine whether the defect affects only the current work unit or also previous architecture, data, contracts and downstream work. Correct and revalidate before propagation.

# 7. Work-unit contract

## 7.1 Required work-unit fields

| Field | Requirement |
| --- | --- |
| ID | Stable identifier such as AUTH-001 or PAY-003 |
| Objective | One coherent engineering outcome |
| Business value | Why the change matters |
| Inputs | Requirements, contracts, designs and existing implementation |
| Dependencies | Validated prerequisites |
| Scope | Included and explicitly excluded work |
| Expected changes | Components, files, contracts, schema and configuration |
| Constraints | Security, compatibility, cost, time and platform limits |
| Acceptance criteria | Observable success conditions defined before implementation |
| Validation | Automated, engineering review and human decision checkpoints |
| Rollback | How the change can be disabled, reversed or recovered |
| Expected output | Code, tests, artifacts, decisions and state updates |

## 7.2 Completion record

- Status: PASS, FAILED or BLOCKED

- Completed scope and changed contracts/files

- Validation performed and result

- Architecture, security, data and deployment impact

- New issues or technical debt

- Project-state updates

- Next dependency-ready work unit

# 8. Validation checkpoint model

| Checkpoint | When required | Examples |
| --- | --- | --- |
| Automated | Every pull request and release | Build, typecheck, lint, unit/integration/E2E, schemas, migrations, security scans, accessibility, performance budgets |
| Engineering review | Architecture/security/data/API changes | Architecture consistency, threat model, dependency impact, code quality, business rules, data model, payment correctness |
| Human decision | High ambiguity, cost, risk or irreversibility | Production release, destructive migration, security incident, payment architecture, risk acceptance, scope/date and legal/privacy decisions |

## 8.1 Pull-request gate

- [ ] Acceptance criteria and dependencies are explicit.

- [ ] Typecheck, lint, tests and production build pass.

- [ ] Security and secret scans pass.

- [ ] Relevant negative and failure-path tests exist.

- [ ] API, schema, configuration and migration changes are documented.

- [ ] Observability and rollback impact are addressed.

- [ ] Project state and architecture decisions are updated where material.

# 9. Environments, branches and release flow

| Environment | Character | Rules |
| --- | --- | --- |
| Development | Local/safe sandboxes | Fast feedback, synthetic data, no live financial or supplier mutation by default |
| Automated test | Isolated/ephemeral | Deterministic fixtures and parallel tests without shared production state |
| Staging | Production-like | Sandbox integrations, migration, E2E, load, recovery and release validation |
| Production | Hardened managed services | Managed secrets, restricted access, monitoring, backups, audit and controlled changes |

## 9.1 Controlled release flow

- Select a dependency-ready work unit and define acceptance criteria.

- Implement on a short-lived branch or controlled trunk workflow.

- Validate locally and open a traceable pull request.

- Run required automated and engineering-review checkpoints.

- Merge only after required checks and approvals pass.

- Build an immutable artifact and deploy automatically to staging.

- Run migrations, smoke tests, E2E, security and release validation.

- Obtain explicit production authorization.

- Deploy progressively where supported; monitor release indicators.

- Record results and roll back when thresholds or acceptance criteria fail.

# 10. Team cadence and control

| Ceremony | Cadence | Required result |
| --- | --- | --- |
| Sprint planning | Every 2 weeks | Select only dependency-ready work units; confirm scope, owner, acceptance and validation |
| Daily update | Working days | Progress, checkpoint result, blocker and next action |
| Architecture/security review | Weekly | Decisions, drift, threats, APIs, data and high-risk changes |
| State/risk review | Weekly | Update PROJECT_STATE, risks, debt, assumptions and next work |
| Sprint review | Every 2 weeks | Demonstrate validated outcomes, not activity or code volume |
| Retrospective | Every 2 weeks | Improve flow, quality, validation and team coordination |
| Phase gate | End of phase | Approve phase completion or record blocking conditions |
| Production review | Before release | Cross-system readiness decision with accountable owners |

# 11. Initial sequenced backlog

| Seq. | ID | Work unit | Depends on | Checkpoint |
| --- | --- | --- | --- | --- |
| 1 | SEC-001 | Rotate exposed supplier credential | None | Human security decision + verification |
| 2 | API-001 | Restrict unsafe supplier proxy methods | None | Security review + abuse tests |
| 3 | STATE-001 | Create persistent project state and risk register | None | Engineering review |
| 4 | ARCH-001 | Document system context and trust boundaries | STATE-001 | Architecture review |
| 5 | AUTHZ-001 | Define roles, permissions and ownership matrix | ARCH-001 | Product + security decision |
| 6 | PAY-001 | Define order/payment state machine | ARCH-001 | Backend + finance decision |
| 7 | DATA-001 | Define core data model and transaction boundaries | ARCH-001 | Data-model review |
| 8 | TEST-001 | Establish unit/component test foundation | STATE-001 | Automated checkpoint |
| 9 | CICD-001 | Create baseline validation pipeline | TEST-001 | Clean pipeline pass |
| 10 | AUTH-001 | Implement verified server-side session/token handling | AUTHZ-001 | Security + integration tests |
| 11 | AUTHZ-002 | Enforce backend RBAC and ownership | AUTH-001, DATA-001 | Negative authorization suite |
| 12 | API-002 | Replace wildcard proxies with explicit endpoints | ARCH-001, AUTH-001 | Contract/security tests |
| 13 | ENV-001 | Define and validate environment contract | ARCH-001 | Startup/configuration tests |
| 14 | OBS-001 | Introduce structured redacted logging | ARCH-001 | Log review + redaction tests |
| 15 | REL-001 | Create staging deployment and immutable release | CICD-001, ENV-001 | Staging smoke test |

# 12. Production approval gate

Approval rule: Production readiness is evidence-based. A target date, successful build or visually complete storefront does not override unresolved blocking conditions.

- [ ] All known critical and high security findings are resolved or formally risk-accepted.

- [ ] Authentication, role and resource-ownership controls pass negative tests at trusted backend boundaries.

- [ ] Prices, discounts, stock, payments and order transitions are server-authoritative and idempotent.

- [ ] Critical unit, integration, contract and end-to-end suites pass.

- [ ] CI/CD produces immutable releases and promotes them through staging.

- [ ] Structured logs, error tracking, metrics, dashboards and alerts are active.

- [ ] Backups are monitored and a restoration exercise meets approved RPO/RTO.

- [ ] Deployment and migration rollback have been rehearsed.

- [ ] Performance, accessibility and security review criteria pass.

- [ ] Incident, supplier, payment and customer-support ownership is assigned.

- [ ] Product, engineering, security, platform, data and payments owners approve release.

# 13. Immediate next action

Begin Phase 0 immediately and create PROJECT_STATE.md in the same work cycle. The exposed supplier credential and unrestricted proxy design are foundational blockers; broader feature work should not propagate on top of them. In parallel, schedule the architecture decisions for session strategy, authorization boundaries, payment/order lifecycle, data ownership and hosting.

## First five controlled actions

- Rotate the exposed supplier credential and confirm the old value is unusable.

- Temporarily block or strictly allowlist supplier proxy operations.

- Create project state, risk register and the first completion records.

- Approve the system-context and trust-boundary diagram.

- Approve roles, permissions, ownership and session strategy before dependent implementation.

# Appendix A - Blueprint alignment

| Blueprint element | Purpose | U-GETMO implementation |
| --- | --- | --- |
| AI-SWE-001 | Defines what a production system must contain | Security, architecture, deployment, observability, reliability, recovery and maintainability gates |
| ORCH-01 | Persistent project state | PROJECT_STATE, ADRs, risks, decisions, debt, validation and next actions |
| ORCH-02 | Dependency-aware work decomposition | Phases, workstreams, sequenced backlog and bounded work-unit contract |
| ORCH-03 | Validation checkpoints | Automated, engineering-review and human-decision gates |
| Controlled autonomy | Approval proportional to risk | Low-risk implementation flows quickly; production, destructive and high-risk decisions require authorization |
| Failure recovery | Stop propagation after failed validation | Diagnose impact, correct, revalidate, update state and only then continue |

# Appendix B - Source references

- AI Software Engineer Blueprint v0.1, AI-SWE-001 - Build Systems, Not Just Features.

- AI Software Engineer Blueprint, AI-SWE-002 - Orchestrate Complex Engineering Work, supplied as C:\Users\dntsi\Downloads\AI Software Engineer Blueprint (1).pdf.

- U-GETMO Production Readiness Assessment produced from the supplied U-GETMO frontend workspace.

- U-GETMO source workspace: C:\Users\dntsi\Downloads\U-GETMO-FE-development (1)\U-GETMO-FE-development.